## Epics
Epic ID | Epic Name | Target Release | Description | Expected Business Value | Priority
EPIC-01 | Unify & Document Support Procedures | Release 1 | Consolidate dispersed, undocumented support procedures into a single knowledge base and standard triage workflow. | Reduced onboarding time; consistent incident handling across shifts | High
EPIC-02 | Mixed-Shore Support Model Transition | Release 2 | Redesign the offshore-only support model into a mixed-shore (onshore + offshore) model with clear ownership and follow-the-sun handoff. | 24/5 coverage with reduced handoff delay; balanced workload | High
EPIC-03 | Unified Support Portal & Escalation Tooling | Release 1 | Replace fragmented tools with a single ticketing/escalation portal integrated with monitoring alerts. | Single source of truth for ticket status; fewer manual errors | High
EPIC-04 | Root Cause Analysis & Continuous Improvement | Release 1 | Establish a recurring Fishbone-based RCA process for top incidents, feeding directly into sprint backlog. | Fewer repeat incidents; data-driven backlog prioritization | Medium
EPIC-05 | Stakeholder Visibility & Reporting | Release 3 | Build a reporting layer giving business stakeholders and leadership real-time visibility into support KPIs. | Improved stakeholder trust; faster leadership decision-making | Medium
EPIC-06 | Design-Thinking-Led Workflow Redesign | Release 2 | Apply persona-based design thinking (personas, To-Be Experience Map) to redesign support workflows around user experience, not just systems. | Improved user satisfaction; workflows built around real user needs | Medium

## User_Stories_Backlog
Story ID | Epic | User Story (As a / I want / So that) | Acceptance Criteria (Given/When/Then) | Sprint | Story Points | Status
US-101 | EPIC-01 | As a support analyst, I want a searchable knowledge base of runbooks, so that I can resolve incidents without relying on tribal knowledge. | Given an application incident, when I search the knowledge base by app name, then I see an up-to-date runbook with resolution steps. | Sprint 1 | 5 | To Do
US-102 | EPIC-01 | As a support manager, I want a standard incident triage workflow, so that priority and severity are assigned consistently across shifts. | Given a new incident, when it is logged, then it is automatically assigned a severity level based on predefined rules. | Sprint 1 | 8 | To Do
US-103 | EPIC-03 | As a support analyst, I want a unified ticketing portal, so that I don't have to check multiple tools to see ticket status. | Given an open incident, when I view the portal, then I see its current status, owner, and history in one place. | Sprint 2 | 8 | To Do
US-104 | EPIC-03 | As a support analyst, I want ticket routing based on the affected application, so that incidents reach the right owner without manual reassignment. | Given an incident is logged with an application tag, when submitted, then it is auto-routed to the correct support queue. | Sprint 2 | 5 | To Do
US-105 | EPIC-02 | As an offshore support analyst, I want a documented handoff checklist, so that onshore teams have full context at shift change. | Given a shift change, when handoff occurs, then the incoming team confirms receipt of a completed handoff checklist for all open incidents. | Sprint 3 | 5 | To Do
US-106 | EPIC-02 | As a support operations manager, I want defined application ownership across shores, so that there is no ambiguity on who resolves an incident. | Given any of the 120+ applications, when an incident occurs, then exactly one owning team is identified without escalation delay. | Sprint 3 | 8 | To Do
US-107 | EPIC-04 | As a support manager, I want a Fishbone-based RCA process for recurring incidents, so that root causes (not just symptoms) are addressed. | Given 3+ recurring incidents on the same application within 30 days, when reviewed, then a Fishbone RCA is documented and linked to a backlog item. | Sprint 2 | 5 | To Do
US-108 | EPIC-05 | As a trading operations stakeholder, I want real-time visibility into ticket status, so that I know an issue is being handled without contacting support directly. | Given an open incident tied to my business line, when I check the reporting dashboard, then I see live status, ETA, and owner. | Sprint 5 | 8 | To Do
US-109 | EPIC-05 | As bank technology leadership, I want a monthly KPI report on incident volume and resolution time, so that I can measure the impact of the mixed-shore transition. | Given a completed month, when the report is generated, then it shows total incidents, average resolution time, and trend vs. prior month. | Sprint 6 | 5 | To Do
US-110 | EPIC-06 | As a support analyst, I want workflows designed around my actual daily tasks, so that I spend less time navigating tools and more time resolving issues. | Given persona research and the To-Be Experience Map, when the new workflow is piloted, then analyst task-switching time is reduced versus the current process. | Sprint 4 | 5 | To Do
US-111 | EPIC-06 | As an onshore business stakeholder, I want a single escalation channel, so that I don't have to guess who to contact for urgent issues. | Given an urgent issue, when I use the designated escalation channel, then I receive acknowledgment within 15 minutes. | Sprint 4 | 3 | To Do
US-112 | EPIC-04 | As a support analyst, I want incidents automatically flagged as recurring, so that I know when a deeper RCA is warranted instead of a quick fix. | Given an incident on an application with 2+ prior incidents in 30 days, when logged, then it is flagged 'Recurring - RCA Required'. | Sprint 3 | 3 | To Do

## INVEST_Validation
INVEST Validation — Sample User Stories
Each story is checked against the INVEST principle before being added to the sprint backlog.
Story ID | Independent | Negotiable | Valuable | Estimable | Small | Testable | Notes
US-101 | Yes | Yes | Yes | Yes (5 pts) | Yes | Yes | Clear given/when/then; no dependency on other stories
US-103 | Yes | Yes | Yes | Yes (8 pts) | Yes | Yes | Slightly larger — monitored for split if needed during sprint planning
US-106 | Partially | Yes | Yes | Yes (8 pts) | Borderline | Yes | Depends on EPIC-01 documentation being complete first; flagged as a sequencing risk, not blocked
US-108 | Yes | Yes | Yes | Yes (8 pts) | Yes | Yes | Requires EPIC-03 portal to be live; scheduled for Sprint 5 accordingly
US-112 | Yes | Yes | Yes | Yes (3 pts) | Yes | Yes | Small, self-contained rule; good candidate for early sprint